## Sheet1
EPIC | User Stories | Core Complexity | UI Complexity | Estimate (MD)
E1. Should be able to manage Self Help Groups
| U1.1 Should be able to create a new Self Help Group | medium | high | 5
| U1.2 Should be able to edit Self Help Group | low | low | 1
| U1.3 Should be able to view a Self Help Group Details | low | low | 1
| U1.4. Should be able to list Self Help Groups | low | low | 1
| U1.5 Should be able to activate a Self Help Group | NA | low | 1
| U1.6 Should be able to attach meeting recurrence to Self Help Group | NA | low | 1
| U1.7 Should be able to create and/or add or remove clients to Self Help Group | NA | medium | 2
| U1.8 Should be able to assign/un-assign staff to SHG | NA | low | 1
| U1.9 Should be able to assign/un-assign role to SHG member | NA | low | 1
| U1.10 Should be able to close SHG | low | low | 1
| U1.11 Should be define fee related to SHG meeting events | medium | NA | 2
| U1.12 Should be define fee related to SHG deposit events | medium | NA | 2
| U1.13 Should be able to manage SHG cycle status (initiate/approve) | medium | medium | 5
E2. Should be able to define constitution for the cycle
| U2.1 Should be able to Create a new Fund | medium | high | 10
| U2.2 Should be able to Edit Fund | medium | medium | 3
| U2.3 Should be able to Remove Fund | low | low | 2
| U2.4 Should be able to View Fund Details | medium | medium | 5
| U2.5 Should be able to List Funds | medium | medium | 5
E3. Should be able process Loan Applications
| U3.1 Should be able to apply for JLG loans | low | medium | 5
| U3.2 Should be able to edit JLG loan application | low | medium | 2
| U3.3 Should be able to view JLG loan application | low | medium | 1
| U3.4 Should be able to approve JLG loan application | low | medium | 1
| U3.5 Should be able to disburse JLG loan application | low | medium | 1
E4. Should be able to collect deposits/loan repayments/fee on each meeting day
| U4.1 Should be able to generate collection sheet for given meeting for a given fund | high | medium | 10
| U4.2 Should be able to view components of collection details | high | medium | 5
| U4.3 Should be able to capture meeting attendance | low | medium | 2
| U4.4 Should be able to capture collections on the meeting for different funds | high | medium | 5
| U4.5 Should be able to list non-loan transactions for a given member | medium | medium | 3
| U4.6 Should be able to reverse non-loan transactions for a given member | medium | low | 2
| U4.7 Should be able to add collection for a given member | medium | low | 2
E5. Should be able to do group deposit/withdraw
| U5.1 Should be able to add group deposit transaction | medium | low | 4
| U5.2 Should be able to add group withdrawal transaction | medium | low | 2
| U5.3 Should be able to list group transactions | medium | medium | 3
| U5.4 Should be able to reverse group transactions | medium | low | 2
| U5.5 Should be able to transfer amounts between different funds | low | medium | 4
E6. Should be able to share-out and close cycle
| U6.1 Should be able to view share-out | very high | medium | 15
| U6.2 Should be able to trigger share-out | very high | medium | 5
E7. Should allow user to exit with individual share out
| U7.1 Should be able to view individual share-out on a given date | high | medium | 5
| U7.2 Should be able to initiate individual share-out on a given date | high | medium | 5
E8. Should be able to see reports for performance of Self Help Groups
To be decided