## Sheet1
Objective | Work item | Applicable | Timeline
1. Develop and deploy policies for data standardization
1.1. Deploy and maintain ONC content standards | 1.1.1. Discuss and agree on standards maintenance schedule | all | dep 1.2
| 1.1.2. Obtain from NLM and Load SNOMED CT 20130730 and US extension 20130930 | all
| 1.1.3. Obtain from Regenstrief and load LOINC 2.38+ | all
| 1.1.4. Negotiate and install support for RxNORM | all
| 1.1.5. Install and test i2b2 tooling at study sites | all
| 1.1.5. Propose timeline for data standardization activities to PCORI | JRC | dep 1.2.2.
| 1.1.6. Discuss and agree on i2b2 standard data models and standards value sets as phased deployment |  | dep 1.2.2.
| 1.1.6.1. Deploy and test phase 1 standard data model within i2b2 at study sites | all
| 1.1.6.1.1. Test and verify EHR data extract functionality | JRC,all
| 1.1.6.1.2. Test and verify i2b2 data load functionality | DC
1.1.6.1.3. Pilot i2b2 data load and assess site data quality
| 1.1.6.1.4. Report data volume metrics to RW | all
1.1.6….
1.2. Negotiate with research group priority semantics and timeline for data standardization | 1.2.1. Inventory high value data set semantics with obesity, breast cancer and ALS teams | JRC
| 1.2.2. Negotiate data model and semantics prioritization with leadership team and post candiate timeline | all
2. Develop and deploy data governance policies | 2.1. Inventory existing research data governance policies and procedures
2.2. Identify existing barriers to shared research data governance policies within sites
2.3. Draft principles for shared data governance and submit to PCORI
2.4…
3. Develop and deploy policies for data comparison and validation | 3.1 Develop data quality metrics by data class |  | dep 1.1.6
| 3.2. Develop data quality and validation scripts/queries |  | dep 3.1
3.3. Draft policies for employment and scheduling of data quality procedures and submit to PCORI
3.4. Schedule and fund data validation procedures for research sites