## Sheet1
Objective | Work item | Applicable | Timeline | Dependencies
1. Develop and deploy policies for data standardization
1.1. Deploy and maintain ONC content standards | 1.1.1. Discuss and inform team re:standards maintenance schedule | GPC STD/DEV | 2014-08-14 | 1.2
| 1.1.2. Obtain from NLM and Load SNOMED CT 20130730 and US extension 20130930 Distribute i2b2 schema enhancement Update GPC i2b2 ontology database | UNMC | 2014-03-15
| 1.1.3. Obtain from Regenstrief and load LOINC 2.38+ Distribute i2b2 schema enhancement Update GPC i2b2 ontology database | UNMC/UW-Mad | 2014-04-01
| 1.1.4. Negotiate and install support for RxNORM/NDFRT Distribute schema enhancement and update GPC i2b2 ontology database | UNMC/KU | 2014-04-15
| 1.1.5. Install and test i2b2 tooling at study sites | all | 2014-03-01
| 1.1.5.1. Identify version requirements and tooling requirements | GPC STD/DEV | 2014-03-01
| 1.1.5.2. Deploy and test i2b2 metadata standards installation across sites | all | 2014-05-01
| 1.1.6. Negotiate data model and semantics prioritization with data standards and leadership teams and post candidate timeline by domain | GPC STD/DEV | 2014-04-01 | 1.2
| 1.1.6.1 Inventory data standardization documents from ONC for STAGE 2 MU | UNMC | 2014-03-15
| 1.1.6.2 Discuss data model and value sets within GPC-DEV | GPC STD/DEV | 2014-03-15
| 1.1.6.3 Discuss data model proposals with PCORI DSSC and align GPC model with PCORI minimal data set | JRC,DC | 2014-04-15
| 1.1.7. Propose procedures and timeline for data standardization activities to PCORI | JRC,DC | 2014-03-15 | 1.2
| 1.1.8. Iteratively design and deploy standard model across sites by data domain | GPC STD/DEV | 3/1/2014-6-1-2014 | 1.2
| 1.1.8.1. PROCEDURE: Test and verify EHR data extract functionality | GPC STD/DEV
| 1.1.8.2. PROCEDURE: Test and verify i2b2 data load functionality | GPC STD/DEV
| 1.1.8.3. PROCEDURE: Pilot i2b2 data load and assess site data quality | GPC STD/DEV
| 1.1.8.4. PROCEDURE: Report data volume metrics including standardization to leadership | GPC STD/DEV | Feb-Mar
1.1.8.01 DOMAIN: Diagnoses/Assessments
1.1.8.02 DOMAIN: Demographics/Patient findings
1.1.8.03 DOMAIN: Laboratory Tests
1.1.8.04 ……
1.2. Negotiate with research group priority semantics and timeline for data standardization | 1.2.1. Inventory high value data set semantics with obesity, breast cancer and ALS teams; feed data sets to standards prioritization | JRC,DC,GPC STD/DEV | 2014-03-01
1.2.2. Review sites data inventories and identify work steps to align with data standardization plan for research project
1.3 Report data standardization plans to PCORI PLATTE |  | JRC | 2014-04-01
2. Develop and deploy data governance policies | 2.1. Inventory existing research data governance policies and procedures
2.2. Identify existing barriers to shared research data governance policies within sites
2.3. Draft principles for shared data governance and submit to PCORI
2.4…
3. Develop and deploy policies for data comparison and validation | 3.1 Develop data quality metrics by data class |  | dep 1.1.6
| 3.2. Develop data quality and validation scripts/queries |  | dep 3.1
3.3. Draft policies for employment and scheduling of data quality procedures and submit to PCORI
3.4. Schedule and fund data validation procedures for research sites