## Sheet1
Objective | Work item | Applicable | Timeline | Dependencies
1. Develop and deploy policies for data standardization
1.1. Deploy and maintain ONC content standards | 1.1.1. Discuss and inform team re:standards maintenance schedule | GPC STD/DEV | 8/1/14-8/14/2014 | 1.2
| 1.1.2.1 Obtain from NLM UMLS metathesaurus; develop, validate and test scripting changes for standardizing ICD-9-CM concept dimension Distribute i2b2 schema enhancement | UNMC;KU | 3/1/14-3/15/14
| 1.1.2.2 Verify ONC guidelines for demographic and patient observables Develop, test and install i2b2 metadata schema for demographics Distribute i2b2 schema enhancement | UNMC;UWMad | 3/1/14-4/1/14
| 1.1.2.3. Obtain from Regenstrief and load LOINC 2.38+ Develop, test and install i2b2 metadata schema for observables Distribute i2b2 schema enhancement | UNMC; UW-Mad;Mcrf | 3/1/14-4/15/2014
| 1.1.2.4. Obtain from NLM and Load SNOMED CT 20130730 and US extension 20130930 Install and test i2b2 schema enhancement: Clinical findings; Events; Situations(history); Organisms Update GPC i2b2 ontology database | UNMC | 3/1/14-4/30/2014
| 1.1.2.5. Obtain RXNorm from NLM and NDRFT from VA Develop, validate and test schema Negotiate and install metadata for RxNORM/NDFRT Distribute schema enhancement and update GPC i2b2 ontology database | UNMC;KU | 4/1/14-5/15/14
| 1.1.5. Install and test i2b2 tooling at study sites | all | 3/1/2014-4/1/14
| 1.1.5.1. Identify version requirements and tooling requirements | GPC STD/DEV | 2/1/14-3/1/2014
| 1.1.6. Negotiate data model and semantics prioritization with data standards and leadership teams and post candidate timeline by domain | GPC STD/DEV | 3/1/2014-6/30/14 | 1.2
| 1.1.6.1 Inventory data standardization documents from ONC for STAGE 2 MU | UNMC | 3/1/14-3/15/14
| 1.1.6.2 Discuss data model and value sets within GPC-DEV | GPC STD/DEV | 3/1/14-5/1/14
| 1.1.6.3 Discuss data model proposals with PCORI DSSC and align GPC model with PCORI minimal data set | JRC,DC | 3/15/14-4/15/14
| 1.1.7. Propose procedures and timeline for data standardization activities to PCORI | JRC,DC | 2014-04-01 | 1.2
| 1.1.8. Iteratively design and deploy standard model across sites by data domain | GPC STD/DEV | 3/1/14-6/30/14 | 1.2
| 1.1.8.1. PROCEDURE: Test and verify EHR data extract functionality | GPC STD/DEV
| 1.1.8.2. PROCEDURE: Test and verify i2b2 data load functionality | GPC STD/DEV
| 1.1.8.3. PROCEDURE: Pilot i2b2 data load and assess site data quality | GPC STD/DEV
1.1.8.4. PROCEDURE: Sites not installing i2b2 standard schema map i2b2 repository data as required
| 1.1.8.4. PROCEDURE: Report data volume and data quality metrics including standardization to leadership | GPC STD/DEV | 3/15/14-7/30/14
1.1.8.01 DOMAIN: Diagnoses/Assessments
1.1.8.02 DOMAIN: Demographics/Patient findings
1.1.8.03 DOMAIN: Laboratory Tests
1.1.8.04 ……
1.2. Negotiate with research group priority semantics and timeline for data standardization | 1.2.1. Inventory high value data set semantics with obesity, breast cancer and ALS teams; feed data sets to standards prioritization | JRC,DC, GPC STUDY TEAMS | 3/1/14-4/15/14
| 1.1.1.1 Study teams propose test scripts to standards team for test query development | GPC STUDY TEAMS | 3/15/14-5/1/14
| 1.2.2. Review sites data inventories and identify work steps to align with data standardization plan for research project | GPC STD/DEV
1.3 Report data standardization plans to PCORI (PLATTE) |  | JRC,DC | 2014-04-01
2. Develop and deploy data governance policies | 2.1. Inventory existing research data governance policies and procedures | GPC STD/DEV | 3/1/14-3/15/2014
| 2.2. Identify existing barriers to shared research data governance policies within sites | GPC STD/DEV | 3/15/14-4/1/14
| 2.3. Draft principles for shared data governance and submit to PCORI | GPC STD/DEV | 4/1/14-5/1/2014
3. Develop and deploy policies for data comparison and validation | 3.1 Develop data quality metrics by data class | GPC STD/DEV | 3/1/14-6/30/14 | dep 1.1.6
| 3.2. Develop data quality and validation scripts/queries | GPC STD/DEV | 3/1/14-6/30/14 | dep 3.1
| 3.3. Draft policies for employment and scheduling of data quality procedures and submit to PCORI | GPC STD/DEV | 2014-06-15
| 3.4. Schedule and fund data validation procedures for research sites | GPC LEADERSHIP | 5/15/14-7/1/14